## Sheet1
Priority | Item | Effort Required (man hours)
Phase I
1 | Business & Data Understanding | 12
2 | Design the ERD, database schema and relationships. | 7
3 | Set up the base SQL schema. | 12
4 | ETL Pipeline | 8
5 | Write and test SQL queries for data extraction. | 5
6 | Data Cleaning/Preparations | 6
7 | Exploratory Data Analysis (EDA) - Python Notebook | 16
8 | Data Visualization using Advanced Libraries (e.g., Seaborn, Bokeh) | 10
9 | Visual Analytics Dashboard (Tableau) | 8
10 | Documentation/Slides | 12 | 96
Phase II
11 | Advance Data Processing | 20
12 | Machine Learning Modelling and Optimization | 30
13 | Experiment Tracking and Monitoring | 5
14 | Deployment as a Graphical User Interface | 15
15 | Documentation/Slides | 10 | 80
Total Time for Phase 1 & 2 |  | 176